## Slide 1: TxDOT Project 0-6894: Guidelines for Design and Operation of U-turns
Project Team Kickoff Meeting
Austin, Texas
October 6, 2015

## Slide 2: Task 1. Project Management
Prepare status reports (monthly)
Project Panel meetings (twice a year)
Document project meetings
Final products and deliverables
  Final Research Report
  Project Summary report
  Self-Calculating Spreadsheet Tool for Safety Prediction
Technical Memoranda at end of each task
5

## Slide 3: Task 2. ID & Explore Factors Affecting U-turn Use and Solutions for When U-turn Demand Exceeds Capacity
Factors Possibly Affecting Capacity
Traffic volumes and patterns
Interchange geometrics
Signal Operation (cycle length, phasing, splits)
Signage (typically yield)
Right-turn demand from the cross-street
Driveway access near the interchange
Downstream entry ramp
  Distance, volume, metered?
6

## Slide 4: Task 2 (Continued).
Factors Possibly Affecting Demand
Lane use/assignment
Nearby development intensity
Proximity and number of nearby driveways
Ramp configuration (Diamond or “X”) and interchange spacing
7

## Slide 5: Task 2 (Continued).
Potential Solutions and Techniques for Improving U-turn Efficiency (Operations Solutions)
Modify signal timing plans to reduce queue length and facilitate access to lanes or bays at the start of each U-turn
Modify signal timing plans to facilitate access to frontage road lanes at the end of each U-turn and/or signalized control of the U-turn approach
Right-turn on red (RTOR) restrictions on cross-street to reduce the conflicts between U-turning and right-turning traffic
8

## Slide 6: Task 2 (Continued).
Potential Solutions and Techniques for Improving U-turn Efficiency (Geometric/Access Solutions)
U-turn bay extensions or added lane(s) to facilitate entry to the U-turn lane
Two-lane U-turn lanes to add capacity for unusually high traffic demand
Access controls or driveway closure near the interchange U-turn lane
Access controls for either the U-turn lane or the right-turn lane from the arterial to remove the conflict between these two movements (painted solid line or barrier)
Acceleration lane for U-turn merge
9

## Slide 7: Task 2. What do we need to do?
Literature Review to ID factors and their relevance
State of the practice assessment (TxDOT Districts)
  Contact traffic operations engineer or design engineer
  Obtain information about factors affecting U-turn use
  Ask about solutions used and tried
  Ask about well-performing and problematic ones
    High / Low crash rates
    High / Low delay
  Try to ID a couple possible study sites from each district
10

## Slide 8: Task 2. Questions for Districts
Insight into factors affecting demand
  Lane use/assignment (specifics)
  Temporary (construction/detours)
  Short-term (freeway wrecks)
Factors affecting capacity
  Geometrics
  U-turn traffic control
    What is typically used in the district?
Ask districts about potential solutions
What documents are used in U-turn design?
11

## Slide 9: Task 3. Determine Demand and Capacity of U-turn Lanes Under Various Conditions
Create simulation models (VISSIM specified in proposal) for >= 25 diamond interchanges
Calibrate to field conditions and run models to get performance measures for U-turns operating in several scenarios:
  # Stops
  Delay
  Queue length
  Throughput
12

## Slide 10: Task 3 (Continued).
Sources of data
  Existing archive of counts and existing models
    Many diamonds in South Texas from San Antonio office
    Some in Houston from Houston office
  Collecting data at additional sites
    Plan to collect data at 10-15 new sites
Data to be collected
  Volumes (per movement)
  Geometrics
  Factors (from task 2)
  Signal timing data
    From controller, maybe real-time performance data
13

## Slide 11: Task 4. Determine Operational Effectiveness of Solutions
Apply solutions to resolve operational issues ID’d at previously selected study sites
  Evaluate effectiveness with VISSIM models
    Get MOEs and compare to results from Task 3
  Field test at two sites
    Non-geometric solutions
    Collect field data like in task 3
    Before vs. after comparison
14

## Slide 12: Task 5. Safety Evaluation of U-turn Designs
Cross-sectional safety analysis for existing U-turn configurations
Qualitative evaluation
  Collision diagrams
  Three years of data
  15 case study locations
Quantitative evaluation
  Larger sample size (>= 60 locations)
  Statistically developed safety performance function to predict # and severity of crashes
  Equations for Self-calculating spreadsheet (Deliverable)
15

## Slide 13: Task 6. Develop & Prepare Guidelines
Develop guidelines for use, design, and operation of U-turn lanes at diamond interchanges
Based on results of previous tasks and feedback from panel
Format should be for possible inclusion in Roadway Design Manual
16

## Slide 14: Task 7. Prepare Project Documentation and Project Close
Develop final report and project summary report (Deliverables)
Produce self-calculating spreadsheet tool for predicting safety of U-turn lanes at diamond interchanges (Standalone product Deliverable)
Conduct close-out meeting
17

## Slide 15: Schedule
* Deliverable at end of each Task 2-6
*** Three Deliverables at end of Task 7
(Final Report, Project Summary Report, Self-calculating spreadsheet Tool)
Task | FY 2016 |  |  |  |  |  |  |  |  |  |  |  | FY 2017 |  |  |  |  |  |  |  |  |  |  | 
 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Task 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Deliverables |  |  |  | * |  |  |  |  |  | * |  |  |  |  | * |  |  | * |  |  | * |  |  | ***
18

## Slide 16: Assistance from TxDOT
Input from Project Panel throughout project
Task 2. Contact with districts (Help identify factors, solutions, and potential sites)
Task 4. Field Evaluations
  Traffic Control
  Assistance in implementing timings in controllers, if timing changes are identified as a solution
  Potential need to procure and install signage, if sign(s) are identified as solution
Task 6. Feedback on guidelines
19

## Slide 17: Extra Notes – Panel Questions
“U-turns” also known at Turnaround Lanes
This project will focus on U-turn lanes at diamond interchanges
Questions to be asked of the districts (input welcomed)
List of factors to be investigated (input welcomed)
Suggestions of study sites?
20

## Slide 18: Next Steps
Complete literature review
Begin contacting districts
  Identify factors
  Identify possible solutions
  Identify potential sites
Develop list of relevant factors to be used in Task 3
21

## Slide 19: Questions?
22